## Slide 1
Scrum Framework to be used on “Pre-Evaluation” Project
Scrum Framework

## Slide 2: General Ceremonies Overview
Sprint Planning
Objective: Define & set the Sprint Goal to be achieved. Commit the user stories to be worked during the sprint always aligned with the team’s velocity. Make any adjustments to the story estimation done previously during the Backlog Grooming.
2. Daily Stand Up
Objective:
Identify obstacles or impediments preventing the team to accomplish the committed user stories.
Measure the team’s progress regarding the Burn Down Chart.
Provide follow up to any commitments done during the previous Sprint Retrospective.
3. Backlog Grooming
Objective: Prepare the Backlog prior to the next sprint by pre estimating user stories alongside the team as well as clarifying the Definition of Done of each user story if needed.
4. Sprint Review
Objective: Overview the completion of committed user stories. Acknowledge unfinished stories for their return to the Backlog. Take in account completed story points for the calculation of the team’s velocity.
5. Sprint Retrospective
Objective: Open the team’s conversation regarding the opportunity areas on the working dynamics held by the team. Create a retrospective backlog/action log to keep track of all action items & commitments for the solving of identified issues.

## Slide 3: Scrum Framework Overview
Sprint Lifecycle
Sprint Planning
Backlog Grooming
Sprint Review & Sprint Retrospective
Beginning of Sprint
Mid Sprint
End of Sprint

## Slide 4: Sprint Planning
Objective: Define & set the Sprint Goal to be achieved. Commit the user stories to be worked during the sprint always aligned with the team’s velocity. Make any adjustments to the story estimation done previously during the Backlog Grooming.
When? | How Long | Expected Output | Assistants
At the Beginning of each Sprint | 1.5 hrs | Sprint Goal Committed User Stories for the current Sprint Sum of projected story points to be completed | All Team Members
Pre Requisites:
User stories for the Sprint should be already pre estimated and prioritized as a result of previous Backlog Grooming session
Meeting Agenda:
Definition of the Sprint Goal by the Product Owner
Validate estimations of desired user stories, clarify doubts if needed
Use reference of the team’s velocity for the commitment of user stories.
Commit Sprint’s User Stories

## Slide 5: Daily Stand Up
Objective:
Identify obstacles or impediments preventing the team to accomplish the committed user stories.
Measure the team’s progress regarding the Burn Down Chart.
Provide follow up to any commitments done during the previous Sprint Retrospective.
When? | How Long | Expected Output | Assistants
Daily | 15 minutes | Identification of obstacles & issues Scheduling of meetings for the in depth discussions of issues Action items regarding retrospective commitments. | All Team Members
Pre Requisites:
Each team member should have already updated progress on Kanban Board
Meeting Agenda:
Overview of Kanban Board
Obstacles discovery for each team member.
Follow up on existing action items.

## Slide 6: Backlog Grooming
Objective: Prepare the Backlog prior to the next sprint by pre estimating user stories alongside the team as well as clarifying the Definition of Done of each user story if needed.
When? | How Long | Expected Output | Assistants
At mid Sprint | 1 hr | Estimated User Stories Acceptance Criteria & DoD for user stories Updated and Prioritized Backlog | All Team Members
Pre Requisites:
Product Owner should have made any required updates to the Backlog
Meeting Agenda:
Overview of added/removed/re prioritized backlog entries
Estimation of at least 1 Sprint worth of User Stories.
Explain & Clarify Definition of Done & acceptance criteria for at least 1 Sprint worth of user stories

## Slide 7: Sprint Review
Objective: Overview the completion of committed user stories. Acknowledge unfinished stories for their return to the Backlog. Take in account completed story points for the calculation of the team’s velocity.
When? | How Long | Expected Output | Assistants
End of the Sprint | 30 min | Accountability of finished user stories Updated Backlog | All Team Members
Meeting Agenda:
Overview of completed user stories throughout the Sprint
Sending back unfinished Sprint user stories to the product backlog
Accountability of accomplished story points
Comparing between estimated velocity vs actual velocity

## Slide 8: Sprint Retrospective
Objective: Open the team’s conversation regarding the opportunity areas on the working dynamics held by the team. Create a retrospective backlog/action log to keep track of all action items & commitments for the solving of identified issues.
When? | How Long | Expected Output | Assistants
End of the Sprint | 30 min | Retrospective Backlog Updated | All Team Members
Meeting Agenda:
Overview of general comments regarding the closing Sprint
Review & update of previously defined retrospective action items
Discovery of new team’s pain points
Updating the retrospective backlog and definition of action items